## RFI Log
HOLABIRD ACADEMY — RFI Log
Project No. 2024-0312 ¦ 1500 Imla Street, Baltimore, MD 21224
RFI # | Date Submitted | Subject | Spec Section | Sheet Ref | Submitted By | Assigned To | Date Required | Date Responded | Status | Days Open
RFI-001 | 2025-07-15 | Foundation depth at Grid B-4 does not match geotech report | 03 30 00 | S-2.01 | Sarah Chen | Paul Whitney | 2025-07-22 | 2025-07-20 | Closed
RFI-002 | 2025-07-18 | Door hardware spec references discontinued Schlage series | 08 71 00 | A-6.01 | Sarah Chen | Robert Marks | 2025-07-25 | 2025-07-28 | Closed
RFI-003 | 2025-07-22 | CMU reinforcement spacing conflicts between plan and detail | 04 20 00 | S-3.02 | Sarah Chen | Paul Whitney | 2025-07-29 | 2025-07-27 | Closed
RFI-004 | 2025-07-25 | Roof drain location conflicts with structural beam at Grid D-6 | 07 52 00 | A-4.01 | Sarah Chen | Robert Marks | 2025-08-01 | 2025-08-04 | Closed
RFI-005 | 2025-07-30 | Exterior curtain wall mullion depth exceeds detail dimension | 08 44 13 | A-5.03 | Sarah Chen | Robert Marks | 2025-08-06 | 2025-08-05 | Closed
RFI-006 | 2025-08-02 | Fire-rated corridor wall assembly not specified at Room 104 | 07 84 13 | A-2.01 | Sarah Chen | Robert Marks | 2025-08-09 | 2025-08-11 | Closed
RFI-007 | 2025-08-05 | Electrical panel clearance insufficient in Mech Room 012 | 26 05 00 | E-2.01 | Sarah Chen | David Posey | 2025-08-12 | 2025-08-10 | Closed
RFI-008 | 2025-08-08 | ADA restroom layout does not meet 60-inch turning radius | 10 21 13 | A-2.03 | Sarah Chen | Robert Marks | 2025-08-15 | 2025-08-18 | Closed
RFI-009 | 2025-08-11 | Structural steel connection detail missing at Grid A-1/C | 05 12 00 | S-4.05 | Sarah Chen | Paul Whitney | 2025-08-18 | 2025-08-15 | Closed
RFI-010 | 2025-08-14 | Confirm exterior brick color selection — spec lists 3 options | 04 20 00 | A-5.01 | Sarah Chen | Robert Marks | 2025-08-21 | 2025-08-25 | Closed
RFI-011 | 2025-08-18 | HVAC duct routing conflicts with sprinkler main at 2nd floor | 23 05 00 | M-2.01 | Sarah Chen | David Posey | 2025-08-25 | 2025-08-22 | Closed
RFI-012 | 2025-08-20 | Elevator pit depth does not match manufacturer requirements | 14 20 00 | A-2.01 | Sarah Chen | Robert Marks | 2025-08-27 | 2025-08-29 | Closed
RFI-013 | 2025-08-22 | Playground equipment foundation loads not provided | 31 00 00 | C-3.01 | Sarah Chen | Paul Whitney | 2025-08-29 | 2025-09-02 | Closed
RFI-014 | 2025-08-25 | Kitchen hood exhaust duct size not shown on MEP drawings | 23 05 00 | M-3.01 | Sarah Chen | David Posey | 2025-09-01 | 2025-08-29 | Closed
RFI-015 | 2025-08-28 | Floor finish transition detail between VCT and carpet | 09 65 00 | A-7.02 | Sarah Chen | Robert Marks | 2025-09-04 | 2025-09-05 | Closed
RFI-016 | 2025-09-01 | Confirm waterproofing membrane extent at foundation walls | 07 11 00 | A-4.03 | Sarah Chen | Robert Marks | 2025-09-08 | 2025-09-10 | Closed
RFI-017 | 2025-09-03 | Light fixture type 'F' not found in electrical schedule | 26 51 00 | E-4.01 | Sarah Chen | David Posey | 2025-09-10 | 2025-09-08 | Closed
RFI-018 | 2025-09-05 | Stair handrail extension length conflicts with ADA code | 05 50 00 | A-3.02 | Sarah Chen | Robert Marks | 2025-09-12 | 2025-09-15 | Open
RFI-019 | 2025-09-08 | Sanitary sewer invert elevation conflicts with civil drawings | 22 05 00 | P-1.01 | Sarah Chen | David Posey | 2025-09-15 | 2025-09-14 | Closed
RFI-020 | 2025-09-10 | Gymnasium floor construction assembly not fully detailed | 09 64 00 | A-7.01 | Sarah Chen | Robert Marks | 2025-09-17 |  | Open
RFI-021 | 2025-09-11 | Fire alarm device locations not coordinated with ceiling grid | 28 31 00 | E-5.01 | Sarah Chen | David Posey | 2025-09-18 |  | Open
RFI-022 | 2025-09-12 | Exterior signage size and mounting height not specified | 10 14 00 | A-5.02 | Sarah Chen | Robert Marks | 2025-09-19 |  | Open
RFI-023 | 2025-09-14 | Loading dock leveler pit dimensions conflict with structural | 11 13 00 | A-2.05 | Sarah Chen | Paul Whitney | 2025-09-21 |  | Open
RFI-024 | 2025-09-15 | Window shade pocket depth insufficient for specified product | 12 24 00 | A-5.04 | Sarah Chen | Robert Marks | 2025-09-22 |  | Open
RFI-025 | 2025-09-16 | Telecom room HVAC cooling capacity appears undersized | 23 05 00 | M-2.02 | Sarah Chen | David Posey | 2025-09-23 |  | Open
Formulas:
Days Open = DATEDIF([Date Submitted],[Date Responded],"d")
Days Open = DATEDIF([Date Submitted],TODAY(),"d")