## Submittal Log
HOLABIRD ACADEMY — Submittal Log
Project No. 2024-0312 ¦ 1500 Imla Street, Baltimore, MD 21224
Sub # | Spec Section | Description | Subcontractor | Date Submitted | Date Required | Date Returned | Status | Action Taken | Resubmit Req | Revision | Notes
001 | 03 30 00 | Concrete Mix Design - 4000 PSI | Smith Concrete LLC | 2025-06-15 | 2025-06-29 | 2025-06-27 | Approved | Approved as Submitted | No | 0
002 | 03 20 00 | Reinforcing Steel Shop Drawings | Smith Concrete LLC | 2025-06-18 | 2025-07-02 | 2025-07-05 | Approved as Noted | Minor mark-ups on bar bending schedule | No | 0 | Revise per architect marks
003 | 05 12 00 | Structural Steel Shop Drawings | Chesapeake Steel Erectors | 2025-06-20 | 2025-07-04 | 2025-07-10 | Revise & Resubmit | Connection details incomplete | Yes | 0 | Missing moment connections at Grid C
003A | 05 12 00 | Structural Steel Shop Drawings - Resubmit | Chesapeake Steel Erectors | 2025-07-18 | 2025-08-01 | 2025-07-30 | Approved as Noted | Approved with minor notes | No | 1
004 | 05 31 00 | Steel Deck Shop Drawings | Chesapeake Steel Erectors | 2025-06-25 | 2025-07-09 | 2025-07-08 | Approved | Approved as Submitted | No | 0
005 | 08 11 13 | Hollow Metal Doors and Frames Schedule | American Door & Hardware | 2025-07-01 | 2025-07-15 | 2025-07-18 | Approved as Noted | 3 frames revised for fire rating | No | 0
006 | 08 71 00 | Door Hardware Schedule | American Door & Hardware | 2025-07-05 | 2025-07-19 | 2025-07-25 | Revise & Resubmit | Lockset function incorrect on 8 doors | Yes | 0 | See RFI-002
006A | 08 71 00 | Door Hardware Schedule - Resubmit | American Door & Hardware | 2025-08-05 | 2025-08-19 | 2025-08-15 | Approved | Corrected per RFI-002 response | No | 1
007 | 07 52 00 | Roofing System Product Data | Atlas Roofing Contractors | 2025-07-08 | 2025-07-22 | 2025-07-20 | Approved | Approved as Submitted | No | 0
008 | 07 62 00 | Sheet Metal Flashing Shop Drawings | Atlas Roofing Contractors | 2025-07-10 | 2025-07-24 | 2025-07-28 | Approved as Noted | Revise coping detail at parapet | No | 0
009 | 08 44 13 | Curtain Wall Shop Drawings | Baltimore Glass Works | 2025-07-12 | 2025-07-26 | 2025-08-02 | Revise & Resubmit | Thermal break detail missing | Yes | 0
009A | 08 44 13 | Curtain Wall Shop Drawings - Resubmit | Baltimore Glass Works | 2025-08-15 | 2025-08-29 | 2025-08-28 | Approved as Noted | Minor notes on sealant joints | No | 1
010 | 08 80 00 | Glazing Product Data and Samples | Baltimore Glass Works | 2025-07-15 | 2025-07-29 | 2025-07-27 | Approved | Approved as Submitted | No | 0
011 | 04 20 00 | Masonry Product Data - Brick and CMU | Capitol Masonry Inc. | 2025-07-18 | 2025-08-01 | 2025-08-05 | Approved as Noted | Brick color confirmed per RFI-010 | No | 0
012 | 09 91 00 | Paint Color Schedule and Samples | Patapsco Painting | 2025-07-20 | 2025-08-03 | 2025-08-01 | Approved | Colors approved by Owner | No | 0
013 | 09 21 16 | Gypsum Board Assembly Details | Harbor Drywall Inc. | 2025-07-22 | 2025-08-05 | 2025-08-08 | Approved as Noted | STC rating documentation required | No | 0
014 | 09 51 00 | Acoustical Ceiling Product Data | National Acoustics | 2025-07-25 | 2025-08-08 | 2025-08-06 | Approved | Approved as Submitted | No | 0
015 | 09 65 00 | Resilient Flooring Product Data | Severn Flooring | 2025-07-28 | 2025-08-11 | 2025-08-12 | Approved | Approved as Submitted | No | 0
016 | 09 68 00 | Carpet Product Data and Samples | Severn Flooring | 2025-07-30 | 2025-08-13 | 2025-08-15 | Approved as Noted | Alternate color for Media Center | No | 0
017 | 10 21 13 | Toilet Compartment Shop Drawings | Harbor Drywall Inc. | 2025-08-01 | 2025-08-15 | 2025-08-18 | Approved | Approved as Submitted | No | 0
018 | 10 28 00 | Toilet Accessories Product Data | Harbor Drywall Inc. | 2025-08-03 | 2025-08-17 | 2025-08-14 | Approved | Approved as Submitted | No | 0
019 | 23 05 00 | HVAC Equipment Submittals - AHU | Bay Area Mechanical | 2025-08-05 | 2025-08-19 | 2025-08-25 | Approved as Noted | Sound data required for units near classrooms | No | 0
020 | 22 05 00 | Plumbing Fixtures Product Data | Dominion Plumbing | 2025-08-08 | 2025-08-22 | 2025-08-20 | Approved | Approved as Submitted | No | 0
021 | 26 05 00 | Electrical Panels and Switchgear | Tri-State Electrical | 2025-08-10 | 2025-08-24 | 2025-08-28 | Approved as Noted | Verify short circuit ratings | No | 0
022 | 10 44 00 | Fire Extinguisher Cabinets | Liberty Fire Protection | 2025-08-12 | 2025-08-26 | 2025-08-24 | Approved | Approved as Submitted | No | 0
023 | 06 10 00 | Rough Carpentry Product Data | Fells Point Carpentry | 2025-08-15 | 2025-08-29 | 2025-09-02 | Approved | Approved as Submitted | No | 0
024 | 07 21 00 | Insulation Product Data | Atlas Roofing Contractors | 2025-08-18 | 2025-09-01 | 2025-08-30 | Approved | Approved as Submitted | No | 0
025 | 07 92 00 | Joint Sealants Product Data | Atlas Roofing Contractors | 2025-08-20 | 2025-09-03 | 2025-09-05 | Approved as Noted | Color samples required for exterior | No | 0
026 | 14 20 00 | Elevator Shop Drawings | ThyssenKrupp Elevator | 2025-08-22 | 2025-09-05 |  | Under Review |  |  | 0 | See RFI-012
027 | 28 31 00 | Fire Alarm System Shop Drawings | Liberty Fire Protection | 2025-09-01 | 2025-09-15 |  | Under Review |  |  | 0
028 | 10 14 00 | Signage Shop Drawings | National Signage Corp. | 2025-09-05 | 2025-09-19 |  | Not Submitted |  |  | 0 | Pending RFI-022 response