HOLABIRD ACADEMY

ELEMENTARY / MIDDLE SCHOOL
1500 Imla Street, Baltimore, MD 21224
Project No. 2024-0312

OAC Progress Meeting #1

Date: 2025-08-05

Location: Holabird Academy Job Site Trailer

Time: 10:00 AM — 11:30 AM

## Attendees

| Name | Company | Role |
| --- | --- | --- |
| Denise Washington | Baltimore City Public Schools | Owner's Representative |
| Angela Brooks | Baltimore City Facilities | Construction Manager |
| Robert Marks | Marks, Thomas Architects | Principal Architect |
| Lisa Fernandez | Marks, Thomas Architects | Architect PM |
| Mike Harrison | Hensel Phelps Construction Co. | GC Project Manager |
| James Kowalski | Hensel Phelps Construction Co. | GC Superintendent |
| Sarah Chen | Hensel Phelps Construction Co. | GC Project Engineer |
| Paul Whitney | Whitney Bailey Cox & Magnani (WBCM) | Structural Engineer |
| David Posey | James Posey Associates | MEP Engineer |

## Agenda / Discussion Items

1. Safety Report

Zero incidents to date. All personnel have completed site orientation. Crane operations beginning next week — crane safety plan reviewed and approved. Reminder: hard hats, vests, and safety glasses required at all times on active work areas.

2. Schedule Update

Project is currently 3 days behind schedule due to unforeseen soil conditions at Building A south wing. Steel delivery on track for September 1. Masonry material lead time confirmed at 6 weeks — order placed for CMU and brick.

3. RFI Status

5 RFIs currently open: RFI-001 through RFI-005. RFI-001 (foundation depth) responded to — revised detail issued. RFIs 002-005 awaiting architect/engineer response. GC requesting responses within 10 business days per contract.

4. Submittal Status

12 submittals submitted to date. 8 approved, 2 approved as noted, 1 revise and resubmit (steel shop drawings — connections incomplete), 1 under review. Steel shop drawing resubmittal expected by August 15.

5. Owner Items

Owner confirmed color selections for interior finishes are due by September 15. Owner is evaluating security camera additions — will issue directive if proceeding.

## Action Items

| # | Action | Responsible | Due Date |
| --- | --- | --- | --- |
| 1 | Respond to RFIs 002-005 | Robert Marks | 2025-08-12 |
| 2 | Resubmit steel shop drawings | Sarah Chen | 2025-08-15 |
| 3 | Submit crane safety plan to CM | James Kowalski | 2025-08-08 |
| 4 | Provide interior finish color selections | Denise Washington | 2025-09-15 |

Next Meeting: Two weeks from above date, same time and location.

Minutes prepared by: Sarah Chen