HOLABIRD ACADEMY

ELEMENTARY / MIDDLE SCHOOL
1500 Imla Street, Baltimore, MD 21224
Project No. 2024-0312

OAC Progress Meeting #2

Date: 2025-08-19

Location: Holabird Academy Job Site Trailer

Time: 10:00 AM — 11:30 AM

## Attendees

| Name | Company | Role |
| --- | --- | --- |
| Denise Washington | Baltimore City Public Schools | Owner's Representative |
| Angela Brooks | Baltimore City Facilities | Construction Manager |
| Robert Marks | Marks, Thomas Architects | Principal Architect |
| Lisa Fernandez | Marks, Thomas Architects | Architect PM |
| Mike Harrison | Hensel Phelps Construction Co. | GC Project Manager |
| James Kowalski | Hensel Phelps Construction Co. | GC Superintendent |
| Sarah Chen | Hensel Phelps Construction Co. | GC Project Engineer |
| Paul Whitney | Whitney Bailey Cox & Magnani (WBCM) | Structural Engineer |
| David Posey | James Posey Associates | MEP Engineer |

## Agenda / Discussion Items

1. Safety Report

Zero recordable incidents. Crane mobilized and operational since August 11. Daily crane inspections logged. 2 near-miss reports filed — both related to material staging in crane swing radius. Corrective action: exclusion zone expanded and additional flagging installed.

2. Schedule Update

Foundation work at Building A south wing complete as of August 18. Slab on grade preparation underway for Area A. Steel erection crew mobilizing for September 1 start. 3-day delay from soil conditions being mitigated through weekend concrete work.

3. RFI Status

RFIs 002 through 007 responded to. RFI-002 resulted in hardware specification revision — resubmittal of door hardware schedule required. 3 new RFIs submitted this period (008, 009, 010). Current open: 008, 009, 010.

4. Submittal Status

Steel shop drawings resubmitted and approved as noted on August 15. Door hardware resubmittal in progress per RFI-002 response. 5 new submittals submitted this period. Total: 20 submitted, 15 approved/approved as noted.

5. Change Order Status

PCO-001 (unforeseen soil conditions, $87,500) submitted July 20 — under review. PCO-002 (owner casework upgrade, $34,200) submitted July 28 — under review. PCO-003 (foundation at B-4, $12,800) — approved, executing as CO-001.

## Action Items

| # | Action | Responsible | Due Date |
| --- | --- | --- | --- |
| 1 | Submit door hardware resubmittal | Sarah Chen | 2025-08-26 |
| 2 | Respond to RFI-008 (ADA restroom) | Robert Marks | 2025-08-26 |
| 3 | Provide geotechnical review for PCO-001 | Paul Whitney | 2025-08-26 |
| 4 | Issue CO-001 for signature | Angela Brooks | 2025-08-22 |

Next Meeting: Two weeks from above date, same time and location.

Minutes prepared by: Sarah Chen