HOLABIRD ACADEMY

ELEMENTARY / MIDDLE SCHOOL
1500 Imla Street, Baltimore, MD 21224
Project No. 2024-0312

OAC Progress Meeting #3

Date: 2025-09-02

Location: Holabird Academy Job Site Trailer

Time: 10:00 AM — 11:30 AM

## Attendees

| Name | Company | Role |
| --- | --- | --- |
| Denise Washington | Baltimore City Public Schools | Owner's Representative |
| Angela Brooks | Baltimore City Facilities | Construction Manager |
| Robert Marks | Marks, Thomas Architects | Principal Architect |
| Lisa Fernandez | Marks, Thomas Architects | Architect PM |
| Mike Harrison | Hensel Phelps Construction Co. | GC Project Manager |
| James Kowalski | Hensel Phelps Construction Co. | GC Superintendent |
| Sarah Chen | Hensel Phelps Construction Co. | GC Project Engineer |

## Agenda / Discussion Items

1. Safety Report

Zero recordable incidents. Total man-hours to date: 18,400. Weekly toolbox talks continuing. Topic this week: fall protection for steel erection and elevated work.

2. Schedule Update

Steel erection began September 1 at Building A Grid A-B. Slab on grade Area A poured August 29 — curing. CMU walls started at Stair Tower 1. One-week delay anticipated on steel delivery for Grid E-H members (fabricator material issue). See separate delay notice.

3. RFI Status

RFI-008 through 010 responded to. 4 new RFIs this period (011-014). Current open: 011, 012, 013, 014. Total RFIs to date: 14.

4. Submittal Status

Door hardware resubmittal (006A) approved August 15. Curtain wall shop drawings (009) returned for revision — thermal break detail missing. 3 new submittals submitted. Total: 25 submitted.

5. MEP Coordination

HVAC duct routing conflict identified at 2nd floor between sprinkler main and ductwork. MEP coordination meeting scheduled for September 5. Architect to provide ceiling height clarification for affected corridor.

## Action Items

| # | Action | Responsible | Due Date |
| --- | --- | --- | --- |
| 1 | Issue notice of delay for steel delivery | Mike Harrison | 2025-09-05 |
| 2 | Resubmit curtain wall shop drawings | Sarah Chen | 2025-09-12 |
| 3 | Conduct MEP coordination meeting | David Posey | 2025-09-05 |
| 4 | Respond to RFIs 011-014 | Robert Marks | 2025-09-09 |
| 5 | Submit elevator shop drawings | Sarah Chen | 2025-09-08 |

Next Meeting: Two weeks from above date, same time and location.

Minutes prepared by: Sarah Chen