HOLABIRD ACADEMY

ELEMENTARY / MIDDLE SCHOOL
1500 Imla Street, Baltimore, MD 21224
Project No. 2024-0312

OAC Progress Meeting #4

Date: 2025-09-16

Location: Holabird Academy Job Site Trailer

Time: 10:00 AM — 11:30 AM

## Attendees

| Name | Company | Role |
| --- | --- | --- |
| Denise Washington | Baltimore City Public Schools | Owner's Representative |
| Angela Brooks | Baltimore City Facilities | Construction Manager |
| Robert Marks | Marks, Thomas Architects | Principal Architect |
| Lisa Fernandez | Marks, Thomas Architects | Architect PM |
| Mike Harrison | Hensel Phelps Construction Co. | GC Project Manager |
| James Kowalski | Hensel Phelps Construction Co. | GC Superintendent |
| Sarah Chen | Hensel Phelps Construction Co. | GC Project Engineer |
| Paul Whitney | Whitney Bailey Cox & Magnani (WBCM) | Structural Engineer |
| David Posey | James Posey Associates | MEP Engineer |

## Agenda / Discussion Items

1. Safety Report

One first-aid incident — minor laceration during rebar tying, treated on site. Safety stand-down conducted September 12 to review hand protection requirements. Total man-hours: 24,200.

2. Schedule Update

Steel erection progressing at Grid C-D. Metal deck installation started at Bay 1-4. CMU walls at Stair 1 at 80% and Gymnasium foundation poured. Slab on grade Area B poured September 16. Steel delivery for Grid E-H now confirmed for September 22 (one week late). Mitigation plan: resequence to gymnasium steel during gap week.

3. RFI Status

8 RFIs currently open (018-025). Total RFIs to date: 25. Response rate averaging 8 business days. Two RFIs (020, 021) are blocking upcoming work — gymnasium floor assembly and fire alarm coordination.

4. Submittal Status

28 submittals submitted, 22 approved/approved as noted, 3 revise and resubmit (all resubmitted), 2 under review, 1 not yet submitted. Elevator shop drawings submitted September 8 — under review.

5. Change Order Status

CO-001 executed ($12,800). CO-002 executed ($22,400 — security cameras). PCO-001, 004, 005, 006, 008 remain under review. Total approved changes to date: $35,200. Total pending: $160,200.

6. Owner Items

Interior finish color selections still pending — due September 15. Owner representative requested schedule for next milestone walkthrough.

## Action Items

| # | Action | Responsible | Due Date |
| --- | --- | --- | --- |
| 1 | Provide interior finish color selections — OVERDUE | Denise Washington | 2025-09-15 |
| 2 | Respond to RFI-020 (gym floor assembly) | Robert Marks | 2025-09-19 |
| 3 | Respond to RFI-021 (fire alarm coordination) | David Posey | 2025-09-19 |
| 4 | Submit winter weather protection plan | James Kowalski | 2025-09-23 |
| 5 | Schedule owner milestone walkthrough | Angela Brooks | 2025-09-23 |
| 6 | Review PCO-001 — geotechnical backup submitted | Denise Washington | 2025-09-23 |

Next Meeting: Two weeks from above date, same time and location.

Minutes prepared by: Sarah Chen