## Daily Report
HOLABIRD ACADEMY — Daily Construction Report
Date: | 2025-09-15 |  | Project No.: | 2024-0312
Weather: | Partly Cloudy |  | High Temp: | 78°F
GC Superintendent: | James Kowalski |  | Report By: | Sarah Chen
WORKFORCE ON SITE
Trade / Company | Foreman | Journeymen | Apprentices | Total | Hours
Smith Concrete LLC | 1 | 6 | 2 |  | 8
Chesapeake Steel Erectors | 1 | 5 | 1 |  | 10
Capitol Masonry Inc. | 1 | 4 | 1 |  | 8
Dominion Plumbing | 1 | 3 | 0 |  | 8
Tri-State Electrical | 1 | 2 | 1 |  | 8
Hensel Phelps Construction Co. — Laborers | 0 | 4 | 2 |  | 8
TOTAL
WORK ACTIVITIES
Activity | Location | Description | % Complete
Slab on Grade | Building A - Area B | Prep for concrete pour — vapor barrier and rebar placement | 90%
Steel Erection | Building A - Grid C-D | Erecting columns and beams at 2nd floor Grid C through D | 40%
CMU Walls | Building A - Stair 1 | Laying CMU block — stair tower 1 first lift to 12'-0" | 60%
Underground Plumbing | Building A - 1st Floor | Sanitary and storm rough-in before slab pour Area C | 70%
Site Utilities | East Parking | Storm drain pipe installation and bedding | 50%