## Daily Report
HOLABIRD ACADEMY — Daily Construction Report
Date: | 2025-09-16 |  | Project No.: | 2024-0312
Weather: | Sunny |  | High Temp: | 82°F
GC Superintendent: | James Kowalski |  | Report By: | Sarah Chen
WORKFORCE ON SITE
Trade / Company | Foreman | Journeymen | Apprentices | Total | Hours
Smith Concrete LLC | 1 | 8 | 2 |  | 10
Chesapeake Steel Erectors | 1 | 5 | 1 |  | 10
Capitol Masonry Inc. | 1 | 4 | 1 |  | 8
Dominion Plumbing | 1 | 3 | 0 |  | 8
Atlas Roofing Contractors | 1 | 2 | 0 |  | 6
Hensel Phelps Construction Co. — Laborers | 0 | 5 | 2 |  | 8
TOTAL
WORK ACTIVITIES
Activity | Location | Description | % Complete
Slab on Grade POUR | Building A - Area B | Concrete pour — 145 CY, pump truck, finish crew | 100%
Steel Erection | Building A - Grid C-D | Continue erection — beam connections at 2nd floor | 45%
CMU Walls | Building A - Stair 1 | Continue CMU — bond beam pour at 4'-0" elevation | 70%
Underground Plumbing | Building A - 1st Floor | Continue sanitary rough-in — testing Wednesday | 80%
Foundation Waterproofing | Building A - North | Touch-up waterproofing per inspection punch list items | 50%