## Daily Report
HOLABIRD ACADEMY — Daily Construction Report
Date: | 2025-09-17 |  | Project No.: | 2024-0312
Weather: | Rain AM / Clearing PM |  | High Temp: | 71°F
GC Superintendent: | James Kowalski |  | Report By: | Sarah Chen
WORKFORCE ON SITE
Trade / Company | Foreman | Journeymen | Apprentices | Total | Hours
Chesapeake Steel Erectors | 1 | 5 | 1 |  | 6
Capitol Masonry Inc. | 0 | 0 | 0 |  | 0
Dominion Plumbing | 1 | 3 | 0 |  | 8
Tri-State Electrical | 1 | 2 | 1 |  | 8
Hensel Phelps Construction Co. — Laborers | 0 | 3 | 1 |  | 4
TOTAL
WORK ACTIVITIES
Activity | Location | Description | % Complete
Steel Erection | Building A - Grid C-D | AM rain delay — resumed erection at 11:00 AM | 48%
CMU Walls | RAIN DAY | Masonry crew stood down — cannot lay block in rain | 70%
Underground Plumbing | Building A - 1st Floor | Interior work — not impacted by weather | 85%
Electrical Conduit | Building A - 1st Floor | Underground conduit installation before slab | 30%