HOLABIRD ACADEMY

ELEMENTARY / MIDDLE SCHOOL
1500 Imla Street, Baltimore, MD 21224
Project No. 2024-0312

CHANGE ORDER — CO-001

Date: 2025-08-15

Change Order Number: CO-001

Original Contract Sum: $27,600,000.00

Net Change by Previously Authorized COs: $0.00

Contract Sum Prior to This CO: $27,600,000.00

Net Change of This CO: $12,800.00

New Contract Sum Including This CO: $27,612,800.00

## Description of Change

Foundation redesign at Grid B-4 per structural engineer's response to RFI-001. The foundation at Grid B-4 was deepened by 3 feet to bear below the unforeseen clay layer. This change order covers the portion of PCO-001 work specifically at Grid B-4 which has been completed and verified. The remaining foundation deepening work across the south wing remains under PCO-001 pending final cost reconciliation.

## Schedule Impact

Three (3) calendar days added to the contract time.

OWNER:

Signature: _________________________

Name: Denise Washington

Date: _________________________

CONTRACTOR:

Signature: _________________________

Name: Mike Harrison

Date: _________________________

ARCHITECT:

Signature: _________________________

Name: Robert Marks

Date: _________________________