## Change Order Log
HOLABIRD ACADEMY — Change Order Log
CO/PCO # | Date | Description | Initiated By | Spec Section | Proposed Amount | Approved Amount | Status | Days Impact | Notes
PCO-001 | 2025-07-20 | Unforeseen soil conditions - additional excavation at Bldg A | GC | 31 23 00 | 87500 | 0 | Pending | 5 | Geotech report did not identify clay layer
PCO-002 | 2025-07-28 | Owner-requested casework upgrade in Media Center | Owner | 12 32 00 | 34200 | 0 | Pending | 0 | Owner directive
PCO-003 | 2025-08-05 | Revised foundation at Grid B-4 per RFI-001 response | Architect | 03 30 00 | 12800 | 12800 | Approved | 3 | CO-001
PCO-004 | 2025-08-12 | Additional fire-rated walls at corridor per code review | Architect | 07 84 13 | 28400 | 0 | Under Review | 0 | Related to RFI-006
PCO-005 | 2025-08-18 | Structural steel connection revision per RFI-009 | Engineer | 05 12 00 | 8900 | 0 | Under Review | 0
PCO-006 | 2025-08-25 | Kitchen hood exhaust duct addition per RFI-014 | Engineer | 23 31 00 | 15600 | 0 | Pending | 2
PCO-007 | 2025-09-02 | Owner-requested security camera additions - 8 locations | Owner | 28 23 00 | 22400 | 22400 | Approved | 0 | CO-002
PCO-008 | 2025-09-08 | Elevator pit modification per manufacturer requirements | Architect | 14 20 00 | 19500 | 0 | Under Review | 5 | Related to RFI-012
CO-001 | 2025-08-15 | Foundation redesign at Grid B-4 | Architect | 03 30 00 | 12800 | 12800 | Executed | 3 | From PCO-003
CO-002 | 2025-09-10 | Security camera additions | Owner | 28 23 00 | 22400 | 22400 | Executed | 0 | From PCO-007
TOTALS: