## G702 Summary
APPLICATION AND CERTIFICATE FOR PAYMENT
AIA Document G702 — Application No. 1
TO OWNER: | Baltimore City Public Schools | PROJECT: | HOLABIRD ACADEMY
| Baltimore City Public Schools |  | 1500 Imla Street, Baltimore, MD 21224
FROM CONTRACTOR: | Hensel Phelps Construction Co. | APPLICATION NO: | 1
| Baltimore, MD | PERIOD TO: | 2025-08-31
VIA ARCHITECT: | Marks, Thomas Architects | PROJECT NO: | 2024-0312

## G703 Schedule of Values
Item | Description of Work | Scheduled Value | Previous Applications | This Period - Work | This Period - Materials | Total Completed | % Complete | Balance to Finish | Retainage
1 | General Conditions | 1850000 | 113689 | 140586 | 17803
2 | Site Work & Demolition | 2100000 | 125802 | 182485 | 11724
3 | Concrete | 3200000 | 147038 | 213391 | 14578
4 | Masonry | 1800000 | 87649 | 96599 | 11331
5 | Structural Steel | 2900000 | 114418 | 94110 | 4753
6 | Carpentry | 680000 | 39678 | 52487 | 7465
7 | Thermal & Moisture Protection | 1450000 | 78679 | 77117 | 4230
8 | Doors, Frames & Hardware | 890000 | 31231 | 33160 | 3077
9 | Glazing & Curtain Wall | 1650000 | 86588 | 126587 | 14013
10 | Finishes | 2100000 | 80724 | 138622 | 20065
11 | Specialties | 420000 | 21761 | 28379 | 863
12 | Equipment | 380000 | 24498 | 22842 | 691
13 | Elevator | 350000 | 21361 | 12230 | 561
14 | Fire Suppression | 680000 | 25715 | 53172 | 2027
15 | Plumbing | 1200000 | 46889 | 61110 | 1419
16 | HVAC | 2800000 | 114915 | 196712 | 7538
17 | Electrical | 2400000 | 88288 | 128491 | 1976
18 | Communications & Security | 750000 | 42777 | 24516 | 243
GRAND TOTAL