## G702 Summary
APPLICATION AND CERTIFICATE FOR PAYMENT
AIA Document G702 — Application No. 2
TO OWNER: | Baltimore City Public Schools | PROJECT: | HOLABIRD ACADEMY
| Baltimore City Public Schools |  | 1500 Imla Street, Baltimore, MD 21224
FROM CONTRACTOR: | Hensel Phelps Construction Co. | APPLICATION NO: | 2
| Baltimore, MD | PERIOD TO: | 2025-09-30
VIA ARCHITECT: | Marks, Thomas Architects | PROJECT NO: | 2024-0312

## G703 Schedule of Values
Item | Description of Work | Scheduled Value | Previous Applications | This Period - Work | This Period - Materials | Total Completed | % Complete | Balance to Finish | Retainage
1 | General Conditions | 1850000 | 174798 | 215536 | 24152
2 | Site Work & Demolition | 2100000 | 282297 | 222623 | 20435
3 | Concrete | 3200000 | 426552 | 191114 | 25147
4 | Masonry | 1800000 | 238694 | 124419 | 5361
5 | Structural Steel | 2900000 | 296852 | 179404 | 24323
6 | Carpentry | 680000 | 53879 | 74348 | 5985
7 | Thermal & Moisture Protection | 1450000 | 118796 | 140844 | 17938
8 | Doors, Frames & Hardware | 890000 | 107894 | 48353 | 6989
9 | Glazing & Curtain Wall | 1650000 | 164863 | 74208 | 7650
10 | Finishes | 2100000 | 214476 | 136099 | 11336
11 | Specialties | 420000 | 53712 | 31296 | 1396
12 | Equipment | 380000 | 37853 | 30044 | 1063
13 | Elevator | 350000 | 41235 | 31262 | 1112
14 | Fire Suppression | 680000 | 68987 | 77766 | 11516
15 | Plumbing | 1200000 | 122012 | 49405 | 2362
16 | HVAC | 2800000 | 392919 | 204903 | 8495
17 | Electrical | 2400000 | 260737 | 269921 | 40034
18 | Communications & Security | 750000 | 100928 | 53306 | 6719
GRAND TOTAL