## Photo Log
HOLABIRD ACADEMY — Progress Photo Log
Photo # | Date | Location | Direction | Description | Taken By | File Name
001 | 2025-08-01 | Building A - East Elevation | West | Existing structure prior to demolition - east facade | Sarah Chen | IMG_001 Existing Structure.jpg
002 | 2025-08-05 | Site - North | South | Site clearing operations - north lot area | Sarah Chen | IMG_002 Site Clearing.jpg
003 | 2025-08-15 | Building A - Grid A-C | North | Excavation for foundations at Grid A through C | James Kowalski | IMG_003 Excavation Grid A.jpg
004 | 2025-08-22 | Building A - Grid B-4 | Down | Rebar placement at foundation Grid B-4 | James Kowalski | IMG_004 Rebar Placement.jpg
005 | 2025-08-28 | Building A - South Wing | North | Foundation walls - south wing complete | Sarah Chen | IMG_005 Foundation Walls.jpg
006 | 2025-09-02 | Building A - Slab Area A | West | Slab on grade preparation - vapor barrier and rebar | Sarah Chen | IMG_006 Slab Prep.jpg
007 | 2025-09-05 | Building A - Slab Area A | West | Slab on grade pour in progress | James Kowalski | IMG_007 Slab Pour.jpg
008 | 2025-09-08 | Building A - Grid A-B | East | First structural steel erected - Grid A-B columns | Sarah Chen | IMG_008 Steel Erection.jpg
009 | 2025-09-10 | Building A - Stair 1 | Up | CMU stair tower walls - first lift complete | Sarah Chen | IMG_009 CMU Stair.jpg
010 | 2025-09-12 | Site - East | West | Storm drain installation - east parking | James Kowalski | IMG_010 Storm Drain.jpg
011 | 2025-09-15 | Building A - Overall | Northwest | Overall site progress - aerial from crane | Sarah Chen | IMG_011 Aerial Overview.jpg
012 | 2025-09-16 | Building B - Gym | South | Gymnasium foundation walls poured | James Kowalski | IMG_012 Gym Foundation.jpg