## 3-Week Lookahead
HOLABIRD ACADEMY — 3-Week Lookahead (Week of 9/15/2025)
Week | Activity | Trade | Location | Resources | Notes | Constraint
Week 1 9/15-9/19 | Slab on grade pour - Area B | Smith Concrete | Building A - South Wing | 8 workers, pump truck | Cure time 7 days | Weather dependent
Week 1 | Structural steel erection - Grid C-D | Chesapeake Steel | Building A - 2nd Floor | 6 ironworkers, crane | Crane setup Monday AM | Crane permit confirmed
Week 1 | CMU walls - Stair Tower 1 | Capitol Masonry | Building A - Stair 1 | 5 masons | Scaffold in place
Week 1 | Underground plumbing rough-in | Dominion Plumbing | Building A - 1st Floor | 4 plumbers | Before slab pour Area C | Coordinate with concrete
Week 1 | Site utilities - storm drain | Site Sub | East Parking Area | 3 operators, excavator |  | Utility locate complete
Week 2 9/22-9/26 | Metal deck installation | Chesapeake Steel | Building A - 2nd Floor Bay 1-4 | 4 workers | After steel at Grid C-D | Steel erection predecessor
Week 2 | Structural steel - Grid E-F | Chesapeake Steel | Building A - 2nd Floor | 6 ironworkers, crane
Week 2 | CMU walls - Gymnasium | Capitol Masonry | Building B - Gym | 8 masons | Bond beam at 4'-0" intervals | Rebar delivery Wed
Week 2 | Electrical underground conduit | Tri-State Electrical | Building A - 1st Floor | 3 electricians | Before slab pour Area C
Week 2 | Foundation waterproofing touch-up | Atlas Roofing | Building A - North Foundation | 2 workers | Per inspection punch list
Week 3 9/29-10/3 | Slab on grade pour - Area C | Smith Concrete | Building A - North Wing | 8 workers, pump truck |  | Plumbing/electrical complete
Week 3 | Structural steel - Grid G-H | Chesapeake Steel | Building A - 2nd Floor | 6 ironworkers
Week 3 | CMU walls continued | Capitol Masonry | Building B - Gym + Stair 2 | 8 masons
Week 3 | HVAC equipment pad prep | Bay Area Mechanical | Mechanical Yard | 3 workers | Housekeeping pads | Equipment delivery 10/6
Week 3 | Temporary enclosure prep | GC Forces | Building A - 2nd Floor | 4 laborers | Winter weather prep | Material order placed