## Master Schedule
HOLABIRD ACADEMY — Master Construction Schedule Rev 3
WBS | Activity | Duration (days) | Start | Finish | Predecessor | % Complete | Status
1.0 | PRECONSTRUCTION
1.1 | Permits & Approvals | 45 | 2025-04-01 | 2025-05-15 |  | 100% | Complete
1.2 | Mobilization | 10 | 2025-05-16 | 2025-05-25 | 1.1 | 100% | Complete
2.0 | SITEWORK
2.1 | Demolition of Existing Structure | 30 | 2025-05-26 | 2025-06-24 | 1.2 | 100% | Complete
2.2 | Mass Excavation | 20 | 2025-06-25 | 2025-07-14 | 2.1 | 100% | Complete
2.3 | Site Utilities | 25 | 2025-07-15 | 2025-08-08 | 2.2 | 85% | In Progress
2.4 | Fine Grading & Paving | 15 | 2025-11-01 | 2025-11-15 | 2.3 | 0% | Not Started
3.0 | FOUNDATIONS
3.1 | Foundation Excavation | 15 | 2025-07-15 | 2025-07-29 | 2.2 | 100% | Complete
3.2 | Foundation Rebar | 12 | 2025-07-30 | 2025-08-10 | 3.1 | 100% | Complete
3.3 | Foundation Concrete Pour | 8 | 2025-08-11 | 2025-08-18 | 3.2 | 100% | Complete
3.4 | Foundation Waterproofing | 10 | 2025-08-19 | 2025-08-28 | 3.3 | 100% | Complete
3.5 | Slab on Grade | 12 | 2025-08-29 | 2025-09-09 | 3.4 | 75% | In Progress
4.0 | STRUCTURE
4.1 | Structural Steel Erection | 35 | 2025-09-01 | 2025-10-05 | 3.3 | 40% | In Progress
4.2 | Metal Deck Installation | 15 | 2025-09-22 | 2025-10-06 | 4.1SS+15 | 10% | In Progress
4.3 | Elevated Concrete Slabs | 20 | 2025-10-07 | 2025-10-26 | 4.2 | 0% | Not Started
4.4 | CMU Walls | 30 | 2025-09-15 | 2025-10-14 | 3.3 | 25% | In Progress
5.0 | BUILDING ENVELOPE
5.1 | Exterior Framing | 20 | 2025-10-15 | 2025-11-03 | 4.4 | 0% | Not Started
5.2 | Curtain Wall Installation | 25 | 2025-11-04 | 2025-11-28 | 5.1 | 0% | Not Started
5.3 | Brick Veneer | 30 | 2025-11-04 | 2025-12-03 | 5.1 | 0% | Not Started
5.4 | Roofing | 20 | 2025-10-27 | 2025-11-15 | 4.3 | 0% | Not Started
6.0 | INTERIOR ROUGH-IN
6.1 | MEP Rough-In — 1st Floor | 30 | 2025-10-15 | 2025-11-13 | 4.4 | 0% | Not Started
6.2 | MEP Rough-In — 2nd Floor | 30 | 2025-11-01 | 2025-11-30 | 4.3 | 0% | Not Started
6.3 | Interior Framing | 25 | 2025-11-14 | 2025-12-08 | 6.1 | 0% | Not Started
6.4 | Drywall & Taping | 20 | 2025-12-09 | 2025-12-28 | 6.3 | 0% | Not Started
7.0 | FINISHES
7.1 | Painting | 20 | 2025-12-29 | 2026-01-17 | 6.4 | 0% | Not Started
7.2 | Flooring | 15 | 2026-01-18 | 2026-02-01 | 7.1 | 0% | Not Started
7.3 | Ceilings | 12 | 2026-01-18 | 2026-01-29 | 7.1 | 0% | Not Started
7.4 | Casework & Specialties | 15 | 2026-02-02 | 2026-02-16 | 7.2 | 0% | Not Started
8.0 | COMMISSIONING & CLOSEOUT
8.1 | MEP Startup & Testing | 15 | 2026-02-17 | 2026-03-03 | 7.4 | 0% | Not Started
8.2 | Punch List | 10 | 2026-03-04 | 2026-03-13 | 8.1 | 0% | Not Started
8.3 | Final Inspections | 5 | 2026-03-14 | 2026-03-18 | 8.2 | 0% | Not Started
8.4 | Substantial Completion | 0 | 2026-03-18 | 2026-03-18 | 8.3 | 0% | Not Started
8.5 | Owner Move-In | 10 | 2026-03-19 | 2026-03-28 | 8.4 | 0% | Not Started