## Correspondence Log
HOLABIRD ACADEMY — Correspondence Log
Date | Type | From | To | Subject | Reference | Action Required | Status
2025-07-10 | Email | Mike Harrison | Robert Marks | Submittal schedule for Division 08 |  | Review schedule | Closed
2025-07-15 | Letter | Mike Harrison | Denise Washington | Notice of commencement |  | Acknowledge | Closed
2025-07-20 | Email | Sarah Chen | Lisa Fernandez | RFI-001 Foundation depth clarification | RFI-001 | Respond by 7/22 | Closed
2025-07-25 | Email | Paul Whitney | Sarah Chen | Response to RFI-001 — revised foundation detail | RFI-001 | Distribute to field | Closed
2025-08-01 | Email | Mike Harrison | Denise Washington | Monthly progress report — July 2025 |  | Review | Closed
2025-08-05 | Email | Lisa Fernandez | Sarah Chen | Submittal 003 returned — revise and resubmit | Sub-003 | Resubmit steel shop dwgs | Closed
2025-08-10 | Email | Mike Harrison | Angela Brooks | Schedule update — steel delivery delayed 1 week |  | Update schedule | Closed
2025-08-15 | Letter | Mike Harrison | Robert Marks | Request for information follow-up — 5 open RFIs | RFI-003,004,005,006,007 | Respond to open RFIs | Closed
2025-08-20 | Email | Denise Washington | Mike Harrison | Owner directive — security camera additions | PCO-007 | Price and schedule impact | Closed
2025-08-25 | Email | Sarah Chen | David Posey | MEP coordination meeting request — 2nd floor conflicts |  | Schedule meeting | Closed
2025-09-01 | Email | Mike Harrison | Denise Washington | Monthly progress report — August 2025 |  | Review | Closed
2025-09-05 | Email | Sarah Chen | Paul Whitney | RFI-023 loading dock pit dimensions | RFI-023 | Respond by 9/21 | Open
2025-09-08 | Email | Mike Harrison | All Subs | Winter weather preparation requirements |  | Submit weather plans | Open
2025-09-10 | Letter | Mike Harrison | Denise Washington | Notice of delay — structural steel delivery |  | Acknowledge | Open
2025-09-12 | Email | Lisa Fernandez | Sarah Chen | Addendum 02 issued — revised exterior details | Add-02 | Distribute & price | Open
2025-09-15 | Email | Sarah Chen | Robert Marks | Submittal 026 — elevator shop drawings submitted | Sub-026 | Review | Open