Date: August 20, 2025

Robert Marks, AIA

Marks, Thomas Architects

Baltimore, MD

RE: HOLABIRD ACADEMY

Project No. 2024-0312

RFI Follow-Up — Outstanding Items

Dear Robert,

We are writing to follow up on five (5) outstanding Requests for Information that remain open beyond the contractually required 10-business-day response period. Timely responses are critical to maintaining the project schedule and avoiding potential delays to the construction activities dependent on these clarifications.

The following RFIs require your immediate attention:

•  RFI-003: CMU reinforcement spacing — submitted 7/22, response due 7/29

•  RFI-004: Roof drain location conflict — submitted 7/25, response due 8/01

•  RFI-005: Curtain wall mullion depth — submitted 7/30, response due 8/06

•  RFI-006: Fire-rated corridor wall assembly — submitted 8/02, response due 8/09

•  RFI-007: Electrical panel clearance — submitted 8/05, response due 8/12

We respectfully request responses to all five items no later than August 27, 2025. Should responses not be received by that date, the contractor reserves the right to submit a request for time extension for any delays attributable to the outstanding design clarifications.

Please do not hesitate to contact us if you require any additional information.

Sincerely,

Mike Harrison

Project Manager

Hensel Phelps Construction Co.