## How to Download
Download (Excel, PDF, etc.) | Create Your Own Copy (Google Sheets)
Select File > Download | Select File > Make a Copy

## Procurement Log Template
Item Description | Quantity | Date Required Onsite | Lead Time (Days) | Required Order Date | Approval Forms | Actual Order Date | Purchase Order # | Delivery Location | Expected Delivery Date | Actual Delivery Date | Receiver | Approval Process | Supplier Contact | Notes/Comments
Door | 10 | 2023-03-04 | 7 | 2023-03-08 | RFI | 2023-03-08 | PO-1234 |  | 2023-03-15 | 2023-03-15 |  | QA |  | None
Window | 20 | 2023-03-04 | 14 | 2023-03-08 | Submittal | 2023-03-08 | PO-4567 |  | 2023-03-22 | 2023-03-29 |  | QA |  | Delayed
Lumber | 100 | 2023-03-04 | 3 | 2023-03-26 | None | 2023-03-26 | PO-7890 |  | 2023-03-29 | 2023-03-28 |  | None |  | None